## Sheet1
Town of Falmouth LPSA Construction - Contract WW-2014-06
Preliminary Schedule - Summary of Work
Preliminary Schedule - Summary of Work
Street/ Location | Descriptor | Start | Finish | Task | Resource Names | Num of Days
Jericho Path/Lake Leaman Rd. | From Falmouth Heights Rd. East to End | 2015-06-15 | 2015-09-25 | Gravity Sewer | Crew #1 | 73
Alma Rd./Falmouth Heights Rd. | Tie in East SMH # 549 | 2015-06-29 | 2015-07-01 | Gravity Sewer | Crew #2 | 3
Russel Rd./Falmouth Heights Rd. | Tie in East to SMH #566 | 2015-07-02 | 2015-07-07 | Gravity Sewer | Crew #2 | 3
Grand Ave. | At Worchester Ct. | 2015-07-06 | 2015-07-20 | Installation of Low Pressure Main (8 days)& Installation of Service Stubs (3 days) | Crew #4 | 11
Russel Rd. | East to Worchester Ct. | 2015-07-08 | 2015-07-27 | Gravity Sewer | Crew #2 | 14
Young Rd./Worchester Ct. | Northeast from Jericho Path (SMH # 572) to SMH #580 | 2015-07-13 | 2015-08-04 | Gravity Sewer | Crew #3 | 17
Elysian Ave. | West of Grand Ave. | 2015-07-21 | 2015-07-31 | Installation of Low Pressure Main (6 days)& Installation of Service Stubs (3 days) | Crew #4 | 9
Alma Rd. | East from SMH #549 to SMH #558 | 2015-07-28 | 2015-08-31 | Gravity Sewer | Crew #2 | 25
Dartmouth Ave. | West of Amherst Ave. | 2015-08-03 | 2015-08-10 | Installation of Low Pressure Main (3 days)& Installation of Service Stubs (3 days) | Crew #4 | 6
Holland St. | South from Lake Leaman (SMH #584) to SMH #599 | 2015-08-05 | 2015-08-18 | Gravity Sewer | Crew #3 | 10
Dartmouth Ct. | East to Hawthorne Ct. | 2015-08-11 | 2015-08-19 | Installation of Low Pressure Main (4 days)& Installation of Service Stubs (3 days) | Crew #4 | 7
Johnson St. | South from Lake Leaman Rd. (SMH #585) to SMH #602 | 2015-08-19 | 2015-08-31 | Gravity sewer | Crew #3 | 9
Hawthorne Ct. | East to Montgonmery Ct. | 2015-08-20 | 2015-08-27 | Installation of Low Pressure Main (3 days)& Installation of Service Stubs (3 days) | Crew #4 | 6
Montgomery Ct. | West to Hawthorne Ct. | 2015-08-28 | 2015-09-08 | Installation of Low Pressure Main (3 days)& Installation of Service Stubs (4 days) | Crew #4 | 7
Worchester Ct. | North from Alma Rd. to End (SMH # 565) | 2015-09-01 | 2015-09-15 | Gravity Sewer | Crew #2 | 10
Sycamore St. | West to Marivista Ave. | 2015-09-01 | 2015-09-11 | Installation of Low Pressure Force Main (5 days) & Installation of Service Stubs (3 days) | Crew #3 | 8
Worchester Ct. | North of Jericho Path & East of Johnson St. | 2015-09-09 | 2015-09-17 | Installation of Low Pressure Main (5 days)& Installation of Service Stubs (2 days) | Crew #4 | 7
Fenton St. | West to Marivista Ave. | 2015-09-14 | 2015-09-23 | Installation of Low Pressure Force Main (5 days) & Installation of Service Stubs (3 days) | Crew #3 | 8
Raymond Rd. | South from Alma Rd. (SMH #555) to SMH #562 | 2015-09-16 | 2015-09-22 | Gravity Sewer | Crew #2 | 5
Jericho Path | South of Lake Leaman Rd. | 2015-09-18 | 2015-09-29 | Installation of Low Pressure Main (5 days)& Installation of Service Stubs (3 days) | Crew #4 | 8
Jericho Path | Southeast from SMH #572 to SMH #631 | 2015-09-23 | 2015-11-20 | Low Pressure Sewer | Crew #2 | 41
Armdore St. | West to Marivista Ave. | 2015-09-24 | 2015-10-06 | Installation of Low Pressure Force Main (5 days) & Installation of Service Stubs (4 days) | Crew #3 | 9
Lucerne Ave. | East of Hudson St. | 2015-09-30 | 2015-10-15 | Installation of Low Pressure Main (5 days)& Installation of Service Stubs (6 days) | Crew #4 | 11
Brockton St. | West to Marivista Ave. | 2015-10-07 | 2015-10-26 | Installation of Low Pressure Force Main (8 days) & Installation of Service Stubs (5 days) | Crew #3 | 13
Miami Ave. | East of Lucerne Ave. | 2015-10-16 | 2015-11-02 | Installation of Low Pressure Main (6 days)& Installation of Service Stubs (6 days) | Crew #4 | 12
Boston St. | West to Marivista Ave. | 2015-10-27 | 2015-11-13 | Installation of Low Pressure Force Main (8 days) & Installation of Service Stubs (5 days) | Crew #3 | 13
Hudson St. | South of Alma Rd. | 2015-11-03 | 2015-11-23 | Installation of Low Pressure Main (3 days)& Installation of Service Stubs (11 days) | Crew #4 | 14
Pocasset St. | West to Marivista Ave. | 2015-11-16 | 2015-11-30 | Installation of Low Pressure Force Main (6 days) & Installation of Service Stubs (3 days) | Crew #3 | 9
Raymond Rd. | North from Lake Leaman Rd. (SMH #589) to End | 2015-11-23 | 2105-12-02 | Gravity Sewer | Crew #2 | 6
Amherst Ave. & Grand Ave | Surrounding Elysian Ave. | 2015-11-24 | 2015-12-07 | Installation of Low Pressure Main (4 days)& Installation of Service Stubs (4 days) | Crew #4 | 8
Spring Bars Rd. | West (Towards Rte. 28)to SMH #505 | 2015-11-25 | 2105-09-09 | Gravity Sewer & Force Main | Crew #1 | 41
Sping Bars Rd. | Force Main | 2015-11-30 | 2015-01-05 | Gravity Sewer & Force Main | Crew #1 | 25
Harmonoy St. | West to Marivista Ave. | 2015-12-01 | 2015-12-14 | Installation of Low Pressure Force Main (6 days) & Installation of Service Stubs (4 days) | Crew #3 | 10
Raymond Rd. | South from Lake Leaman Rd. (SMH #589) to End (SMH #613) | 2015-12-03 | 2015-12-14 | Gravity Sewer and Low Pressure Sewer | Crew #2 | 8
Hudson Rd. | North from Lake Leaman Rd. (SMH #590) to End (SMH #596) | 2015-12-15 | 2015-12-23 | Gravity Sewer | Crew #2 | 7
Massasoit St. | West to Marivista Ave. | 2015-12-15 | 2015-12-28 | Installation of Low Pressure Force Main (5 days) & Installation of Service Stubs (4 days) | Crew #3 | 9
Hudson Rd. | South from Lake Leaman Rd. (SMH #590) to End (SMH #615) | 2015-12-24 | 2015-12-30 | Gravity Sewer and Low Pressure Sewer | Crew #2 | 4
Hamilton St. | West to Marivista Ave. | 2015-12-29 | 2016-01-12 | Installation of Low Pressure Force Main (6 days) & Installation of Service Stubs (4 days) | Crew #3 | 10
Lucerne Ave. | North from Lake Leaman Rd. (SMH #559) to End (SMH #561) | 2015-12-31 | 2016-01-06 | Gravity Sewer and Low Pressure Sewer | Crew #2 | 4
Spring Bars Rd. | East to Marivista Ave. | 2016-01-06 | 2016-02-05 | Force Main & Gravity Sewer | Crew #1 | 22
Lucerne Ave. | South from Lake Leaman Rd. (SMH #559) To End (SMH #617) | 2016-01-07 | 2016-01-11 | Gravity Sewer and Low Pressure Sewer | Crew #2 | 3
Worchester Ct. | South from Lake Leaman Rd. (SMH #587) to End (SMH #610) | 2016-01-12 | 2016-01-20 | Gravity Sewer | Crew #2 | 6
Lawrence St. | West to Marivista Ave. | 2016-01-13 | 2016-01-28 | Installation of Low Pressure Force Main (7 days) & Installation of Service Stubs (4 days) | Crew #3 | 11
Worchester Ct. | South up from Lake Leaman Rd. (SMH #586) to End (SMH #606) | 2016-01-21 | 2016-02-03 | Gravity Sewer | Crew #2 | 10
Providence St. | West to Marivista Ave. | 2016-01-29 | 2016-02-16 | Installation of Low Pressure Force Main (7 days) & Installation of Service Stubs (5 days) | Crew #3 | 12
Randolph St. | East to Marivista Ave. | 2016-02-04 | 2016-02-22 | Low Pressure Sewer | Crew #2 | 12
Marivista Ave. | North to End (SMH #646) | 2016-02-08 | 2016-04-26 | Gravity Sewer | Crew #1 | 55
Hiawatha St. | West to Marivista Ave. | 2016-02-17 | 2016-03-02 | Installation of Low Pressure Force Main (7 days) & Installation of Service Stubs (4 days) | Crew #3 | 11
Oak St. | East and West to Marivista Ave. | 2016-02-23 | 2016-03-21 | Low Pressure Sewer and Gravity Sewer | Crew #2 | 20
Maple St. | East to Marivista Ave. | 2016-03-03 | 2016-03-21 | Installation of Low Pressure Force Main (8 days) & Installation of Service Stubs (5 days) | Crew #3 | 13
Priscilla St | East and West to Marivista Ave. | 2016-03-22 | 2016-04-22 | Low Pressure Sewer and Gravity Sewer | Crew #2 | 23
Palm St. | East to Marivista Ave. | 2016-03-22 | 2016-04-08 | Installation of Low Pressure Force Main (9 days) & Installation of Service Stubs (5 days) | Crew #3 | 14
Narragansett St. | East to Marivista Ave. | 2016-04-11 | 2016-05-02 | Installation of Low Pressure Force Main (10 days) & Installation of Service Stubs (5 days) | Crew #3 | 15
Chestnut St. | East and West to Marivista Ave. | 2016-04-25 | 2016-06-01 | Low Pressure Sewer and Gravity Sewer | Crew #2 | 27
Marivista Ave. | South from Iroquois St. to End | 2016-04-27 | 2016-06-06 | Low Pressure Sewer | Crew #1 | 28
Mayflower St. | East to Marivista Ave. | 2016-05-03 | 2016-05-25 | Installation of Low Pressure Force Main (10 days) & Installation of Service Stubs (7 days) | Crew #3 | 17
Reynolds St. | East to Marivista Ave. | 2016-05-26 | 2016-06-17 | Installation of Low Pressure Force Main (10 days) & Installation of Service Stubs (6 days) | Crew #3 | 16
Bradford St. (Should be Bedford?) | West to Marivista Ave. | 2016-06-02 | 2016-06-17 | Gravity Sewer | Crew #2 | 12
Alphonse St. | West to Rt. 28 | 2016-06-06 | 2016-06-10 | Gravity Sewer & Force Main | Crew #1 | 4
Rt. 28 | South from Alphonse St. to End (SMH #524) | 2016-06-13 | 2016-07-18 | Gravity Sewer& Force Main & Low Pressure Sewer | Crew #1 | 35 (5 weeks)
Stower St. | East to Marivista Ave. | 2016-06-20 | 2016-07-05 | Low Pressure Sewer and Gravity Sewer | Crew #2 | 11
Toledo St. | East to Marivista Ave. | 2016-06-20 | 2016-07-12 | Installation of Low Pressure Force Main (10 days) & Installation of Service Stubs (6 days) | Crew #3 | 16
Swallow St. | West to Marivista Ave. | 2016-07-06 | 2016-07-19 | Low Pressure Sewer and Gravity Sewer | Crew #2 | 10
Rt. 28 | North from Alphonse St. to End (SMH #535) | 2016-07-19 | 2016-07-22 | Gravity Sewer | Crew #1 | 4
Short St. | West off Marista Ext | 2016-07-20 | 2016-07-25 | Low Pressure Sewer and Gravity Sewer | Crew #2 | 4
Rt. 28 | Services from SMH #524 to SMH #535 | 2016-07-25 | 2016-08-19 | Gravity Sewer& Force Main & Low Pressure Sewer | Crew #1 | 20
Village Ln. | West off Marista Ext | 2016-07-26 | 2016-08-11 | Gravity Sewer | Crew #2 | 13
Hitching Post Ln. and Hickory Ln. | West off Marista Ext | 2016-08-12 | 2016-08-18 | Low Pressure Sewer and Gravity Sewer | Crew #2 | 5
Harrington St. | East and West to Marivista Ave. | 2016-08-19 | 2016-09-19 | Low Pressure Sewer and Gravity Sewer | Crew #2 | 21
Rt. 28 | Force Main | 2016-08-22 | 2016-09-19 | Force Main | Crew #1 | 20
Alphonse St. | Force Main | 2016-09-20 | 2016-09-21 | Force Main | Crew #1 | 2
Montauk St. | East and West to Marivista Ave. | 2016-09-20 | 2016-10-17 | Low Pressure Sewer and Gravity Sewer | Crew #2 | 19
Teaticket School | Connection from Alphonse St. Pump Station to SMH #543 | 2016-09-22 | 2016-09-27 | Gravity Sewer | Crew #1 | 4
Cypress St. | East and West to Marivista Ave. | 2016-10-18 | 2016-11-14 | Low Pressure Sewer and Gravity Sewer | Crew #2 | 19
Philadelpia St. | East to Marivista Ave. | 2016-11-15 | 2016-11-30 | Gravity Sewer | Crew #2 | 10
Bourne St. | East to Marivista Ave. | 2016-12-01 | 2016-12-09 | Gravity Sewer | Crew #2 | 7
Cedar St. | East and West to Marivista Ave. | 2016-12-12 | 2016-12-20 | Low Pressure Sewer and Gravity Sewer | Crew #2 | 7